## Country coordination
GMGs Country Co-ordination Spreadsheet |  | KEY: | Programme in Development |  | ESMAP 10 Pillars | KEY: | Significant Progress Made
2020-12-07 |  |  | Programme Approved |  | Preliminary Assessment |  | More Work Needed
|  |  | Building grids now |  |  |  | No Progress To Date
Country | SEFA/AfDB Support | ESMAP/WB Support | Other FCDO Support Summary | Other Donor Support Summary | Solar Hybrid Technology | Geospatial Planning | Productive Uses | Community Engagement | Local & Int'l Industry | Access to Finance | Training & Skills | Institutional Framework | Workable Regulations | Business Environment
Angola | A potential GMG Country Support Package is at identification stage. A market intelligence report will be published in 2020, at: https://greenminigrid.afdb.org
Burkina Faso | A package of TA includes developing an appropriate GMG strategy, regulatory framework, technical standards and guidelines; (ii) assessing existing diesel-powered mini-grids and proposing a plan for their hybridization; (iii) conducting feasibility studies for selected new sites; (iv) developing a financial and commercial framework for private sector investment; (v) developing the capacity of government institutions and other stakeholders in GMGs. This TA includes specific linkages to AfDB's Yeleen mini-grid programme, which is at pre-selection stage and which has processing issues that the TA is expected to addresss. A market intelligence report was published in 2017, at: https://greenminigrid.afdb.org | $17 million for mini grids under the Electricity Sector Support Project approved in 2013; pipeline mini grid investment as part of the Electricity Access Project currently under preparation. Under Component 2 of the Electricity Sector Support Project (Increasing Electricity Access in Target Areas), works are being finalized to serve 80 localities through mini grids and main grid extension. Pipeline project under preparation: Renewable Energy and Access Project. | FCDO appraising options for support to mini-grid development in G5 Sahel Countries (Burkina Faso, Chad, Mali, Mauritania, and Niger) |  | Solar hybrid mini grids are not a new concept in Burkina Faso, but most systems today are diesel only. A global survey by AMDA revealed only 8 companies currently operating in Burkina Faso that, collectively, could have about 113 50kW solar hybrid systems available in 3 months. This is small compared to the country’s market potential. | A national least-cost electrification plan using geospatial analysis was produced by the European Commission in 2016. This report identifies solar hybrid mini grids as the most appropriate option for electrification, but it is not clear how this has informed government policy. It is also not clear whether mini grid developers in Burkina Faso use geospatial analysis when planning their portfolios. | To date we are not aware of any large-scale or developer-led initiatives to promote productive uses of electricity on mini grids in Burkina Faso. | To date we are not aware of any large-scale or developer-driven initiatives to engage with communities served by mini grids in Burkina Faso. | The local mini grid industry is dominated by local cooperatives, though it is unclear whether or how many of these have strong ties with larger international firms. | The WB has committed $17 million to mini grids, with an additional $13 million in the pipeline. Other donors remain active in the electrification space in the country, though not necessarily for solar hybrid mini grids. To date we are not aware of any significant private sector investor interest in the Burkina Faso mini grids market. | We are not aware of any large-scale training programs for mini grid operators, engineers, or maintenance workers, though local cooperatives presumably have informal training programs for local technicians and work crews. | There is a relatively strong institutional framework that can support mini grids in Burkina Faso, with a rural electrification agency ABER and a ministry of energy that are both supportive of mini grids, and professionalized local electricity cooperatives that have a relatively good track record of developing and operating mini grids. | With a RISE score for mini grids of 42/100, Burkina Faso is in the bottom half of countries in Africa for mini grid regulatory framework. Private sector mini grids are allowed, but key issues such as cost-reflective tariffs, main grid arrival, and service and technical standards remain undeveloped or unclear. The mini grid market would benefit from a more coherent regulatory framework. | Bureaucratic red tape remains a barrier to investment and a significant cost to businesses across Burkina Faso. With a Doing Business score of 51/100, the country ranks among the lower-middle set of economies in Africa in terms of starting up and operating a business.
Burundi |  | $37 million for mini grids under the Solar Energy in Local Communities approved in 2020. Project used ESMAP-supported geospatial mapping, which identified 150 potential sites.
Cameroon | A market intelligence report was published in 2017, at: https://greenminigrid.afdb.org | $19 million for mini grids under the Rural Electricity Access Project for Underserved Regions program approved in 2018.
Chad | A market intelligence report will be published in 2020, at: https://greenminigrid.afdb.org | "Chad First Energy Access and Fiscal Management Development Policy Financing" project under preparation | FCDO appraising options for support to mini-grid development in G5 Sahel Countries (Burkina Faso, Chad, Mali, Mauritania, and Niger) |  | With fewer than 10 known mini grids in Chad, solar hybrid technologies are pre-emergent. There was only one company that responded to the AMDA survey of in-country solar hybrid technology inventories, which had sufficient inventory for only one 50kW system within 3 months. | Recent geospatial planning work supported by the World Bank is laying the groundwork for a national least-cost electrification strategy. | To date we are not aware of any large-scale or developer-led initiatives to promote productive uses of electricity on mini grids in Chad. | To date we are not aware of any large-scale or developer-driven initiatives to engage with communities served by mini grids in Chad. | To our knowledge, there is neither a local mini grid industry nor partnerships between local and international firms to develop mini grids in Chad. | Alongside FCDO, the WB is preparing a significant investment in mini grids in the five G5 Sahel countries (final amount TBD). It is not yet clear how much of the total project amount will be committed to Chad. To date we are not aware of any significant private sector investor interest in Chad’s mini grids market. | We are not aware of any large-scale training programs for mini grid operators, engineers, or maintenance workers, though the national utility presumably has formal or informal training programs for its technicians and work crews. | Chad’s energy sector is characterized by weak governance. However, a major focus of the pipeline G5 Sahel Countries project is strengthening institutional frameworks, and it is expected that Chad will be a key focal country for this support. | With a RISE score for mini grids of 37/100, Chad is ranked near the bottom of list of all countries for which mini grid regulatory framework information is available. In parallel with efforts to strengthen the institutional framework, significant work will also be needed to develop a coherent, workable approach to mini grid regulations. | Bureaucratic red tape remains a significant barrier to investment and a major cost to businesses across Chad. With a Doing Business score of 37/100, the country ranks near the bottom of all countries worldwide in terms of the ease with which companies can start up and operating a business.
Cote d'Ivoire | A market intelligence report was published in 2019, at: https://greenminigrid.afdb.org
DRC | A package of TA includes support for solar mini-grid projects developed under the ESSOR program. In particular: finalizing feasibility studies, conducting ESIA, and supporting other late development stage tasks to bring ESSOR’s first three pilot projects to financial closure. A second phase of the ESSOR project will be prepared with further feasibility studies. AfDB BoD and GCF approved co-financing loans of USD 20 million each in March 2019. 3 pilot sites of large GMGs (3-10MW) have been identified. Winner of tender announced in November. A market intelligence report was published in 2017, at: https://greenminigrid.afdb.org | $47 million for mini grids under the Electricity Access & Services Expansion (EASE) program approved in 2017. An ESMAP-funded study will help identify a short list of mini grid sites for investment under EASE. "Electricity & Water Access and Governance Project" currently under preparation. | Essor programme - managing the auction of 3 large mini-grid sites for GoDRC, aligning multiple funders. Winner of Auction announced Nov 20. |  | A global survey by AMDA revealed only 10 companies currently operating in the DRC that, collectively, could have about 135 50kW solar hybrid systems available in 3 months. This is quite small compared to the market potential for solar hybrid systems in the country. | ESMAP and World Bank are supporting the government of the DRC to develop a national least-cost electrification plan (in progress), which builds on the “Country Action Plan” developed under the SE4All initiative with assistance from the AfDB. | To date we are not aware of any large-scale or developer-led initiatives to promote productive uses of electricity on mini grids in the DRC. | To date we are not aware of any large-scale or developer-driven initiatives to engage with communities served by mini grids in the DRC. | There is just a small handful of mini grid developers operating in the DRC that have partnered with larger international firms or investors. Significant work is needed to catalyze the local market and develop linkages with larger international companies. | The WB is preparing a large investment (amount TBD) for mini grids, which builds on the existing $47 million EASE project. Discussions are already ongoing between investors and a small number of developers, and there is interest from investors in the DRC mini grid market in general, but we are not aware of any large-scale deals or commitments to date. | We are not aware of any large-scale training programs for mini grid operators, engineers, or maintenance workers, though the national utility SNEL provides in-house training to its technicians and work crews. | The Ministry of Energy and Water Resources is responsible for the energy sector, which now has a dedicated unit to manage donor-funded projects. The utility SNEL is also an important stakeholder, and since 2014 no longer has a national monopoly on electricity generation and distribution. However, mini grids do not yet have a strong institutional “champion”. | The national electricity regulator (ARE) is not yet operational. Rules for mini grids are embedded in the developer’s concession agreement. Investors have cited the lack of formal regulations as a key risk. DRC’s RISE score is 42/100, among the bottom half of all countries in the RISE database. More work is needed to strengthen the regulation by contract approach and/or formal mini grid regulations. | With a Doing Business score of 36.2/100, the DRC is among the lowest-ranked countries in the world in terms of ease of starting up and operating a business. Significant work is needed to make it easier for private sector mini grid companies to invest in portfolios of viable projects.
Ethiopia | AfDB restructured part (USD 15 million) of an existing sovereign loan to fund the implementation of public sector GMG pilots to be implemented by the national utility, EEU. A tender has been launched. A market intelligence report was published in 2017. A second report focusing on GMG tariffs in Ethiopia will be published in 2020. https://greenminigrid.afdb.org Pipeline under preparation: AfDB is preparing a financing facility to support the energy access sector in Ethiopia. This will likely take the form of a line of credit to a domestic financial institution for the funding ofenergy access companies. SEFA is assessing the potential to support innovative GMG business model pilots at the ag-energy nexus in Ethiopia. | $8 million for mini grids under the ELEAP program approved in 2018. A significantly larger investment for mini grids is currently under preparation. For the ELEAP project: EEU advanced site preparation and procurement (bidding and contracts signing) for the electrification of 12 rural towns/villages through solar mini grids, of which 5 will be verified by the Program once installed. Currently, EEU is advancing ESIAs and audit on land acquisition for all sites. Pipeline project under preparation: Accelerating Distributed Electricity and Lighting in Ethiopia (ADELE) | Keen interest in mini-grids at Africa Investment Summit, country office following up. |  | A global survey by AMDA revealed only 5 companies currently operating in Ethiopia that, collectively, could have about 36 50kW solar hybrid systems available in 3 months. This is quite small compared to the market potential for solar hybrid systems in the country. | The World Bank is currently supporting the government of Ethiopia to use geospatial analysis to identify hundreds of high potential mini grid sites across the country. | An extensive analysis of the microfinance and income-generating appliance market in Ethiopia was recently completed. It revealed a large and vibrant market for income-generating machines and appliances, and a microfinance market that can support a large-scale productive uses program. The next step is implementing a national program to connect end users with appliances and finance. | We are not aware of any large-scale community engagement efforts by EEU or the national government, or local-level community engagement efforts by mini grid developers or EEU. | The mini grid market in Ethiopia has remained relatively closed to private sector developers to date. There are a handful of companies that have solar hybrid mini grid components in country, according to data from the AMDA survey, but significant work is needed to grow a local mini grid industry and to facilitate deal-making between local players and international firms. | The WB is preparing a large investment of more than $130 million for mini grids, which is expected to leverage an additional $130 million from development partners and private sector investors. While a small number of private sector investors have expressed interest in the Ethiopian mini grid market, no deals or commitments have yet been made. | We are not aware of any large-scale training programs for mini grid operators, engineers, or maintenance workers, though EEU provides in-house training to its technicians and work crews. | The REA has established an exceptional team to lead the national mini grids program, achieving impressive results already. There is broad support from senior government officials for mini grids. In general the institutional setup for mini grids is coherent and conducive to the NEP’s private-sector led approach. | While regulations for private sector mini grids are still under development, the overall mini grid framework in Ethiopia has a RISE score of 70/100 – one of the highest scores in Africa. Continued support will be needed to ensure that the private sector mini grid regulations are compatible with the combined public- and private-sector approaches envisioned for the country. | With a “Doing Business” score of 48/100, Ethiopia is in the lower-middle of the pack for countries in Africa in terms of the ease with which companies can start up and operate a business. As the market for private sector mini grids begins to open, the risk of creating overly burdensome bureaucracies will need to be mitigated by targeted efforts to streamline bureaucratic processes.
Gabon |  | $9 million for mini grids under the Access to Basic Services in Rural Areas and Capacity Building Project approved in 2015.
Gambia | A package of TA support includes developing a GMG policy, strategy, and regulatory framework; technical standards and guidelines; feasibiltiy studies, and ESIA studies for specific GMG sites; and developing tender documentation for GMG deployment.
Ghana | AfDB RE department programme under appraisal which includes a component of financing for mini-grids. Programme anticipated to receive board approval in 2021. | 5 mini grids built under the GEDAP project (which is nearing its closing date). ESMAP/WB co-hosted events in March 2017 and June 2019.
Guinea | A package of TA focused on enabling green mini-grid projects identified in the low-cost electrification plan (total of 57 sites). This activity is being developed in collaboration with the African Development Bank (AfDB), the World Bank and the Agence Française de Développement (AFD). A market intelligence report will be published in 2020, at: https://greenminigrid.afdb.org | $4 million for mini grids under the Electricity Access Scale Up Project approved in 2019. The mini grids component is progressing satisfactorily. A longlist of potential private operators for mini grids is encouraging. Next steps including the establishment of a short list of operators, validation of interim regulations that will govern concessions of mini-grids under the project and launching of Requests for proposals. At the same time a set of regulations will be prepared to govern future mini grid development activities.
Guinea-Bissau
Kenya |  | $10 million for mini grids under the KEMP project approved in 2015. Under KEMP: Feasibility study and Environmental and Social Assessment (ESSA) studies for the mini-grid sites took longer than expected. After their completion, bidding for the mini grids has been successfully concluded and the contractor has now been selected for construction and operation of the mini grids. The mini-grids are expected to be operational by June 2021. $40 million for mini grids under the KOSAP project approved in 2017. Under KOSAP: site profiling work for all 151 sites have been completed and bidding document is at final stage of preparation. | Green Mini-Grids Kenya programme in operation, now also with EU ITF Funding in second round, supporting 4 developers now - 8000 connections delivered so far. Mini-Grid RBF programme with EnDev recently finished delivering 10 GMGs and 1800 connections.
Lesotho |  | $20 million for mini grids under the Renewable Energy and Energy Access Project approved in 2020.
Liberia |  | $21 million for mini grids approved in the Renewable Energy Access Project in 2016. Bidding for the large hydropower mini grid, a key activity under the project, has been completed and recommendation for award of contract cleared by the Bank.
Madagascar | A workshop was held with GMG market stakeholders in December 2019, and a market intelligence report was published in 2019, at: https://greenminigrid.afdb.org |  | FCDO supporting pilot of Universal Energy Facility led by SEforALL alongside Rockefeller, USAID, and Shell Foundation. Madagascar and Sierra Leone pilot countries.
Malawi |  | $10 million for mini grids under the Electricity Access Project approved in 2019.
Mali | A market intelligence report was published in 2019. A second market intelligence report assessing mini-hydro opportunities in Mali will be published in 2020, at: https://greenminigrid.afdb.org | $51 million for mini grids under the Rural Electrification Hybrid System Project approved in 2013. Six hybrid systems have been completed and are undergoing commissioning testing. | FCDO appraising options for support to mini-grid development in G5 Sahel Countries (Burkina Faso, Chad, Mali, Mauritania, and Niger) |  | Mali is a regional leader in solar hybrid mini grid technologies, with significant investment over the past decade in hybridizing diesel-only mini grids. This is not fully reflected in the AMDA survey results, which showed only 5 companies with in-country inventory capable of building 17 50kW systems in 3 months. | To our knowledge, the government of Mali does not have a national electrification plan based on geospatial analysis to indicate least-cost options. We are also not aware of any private sector developers in Mali using geospatial analysis to plan their portfolios. | The World Bank’s Africa Gender and Energy Program has worked to support gender integration in rural energy with the government of Mali through its Agency for the Development of Household Energy and Rural Electrification (AMADER), to ensure that the different needs of men and women are taken into account in rural electrification efforts. | To date we are not aware of any large-scale or developer-driven initiatives to engage with communities served by mini grids in Mali, though productive use programs and training programs have been implemented in communities in the past. | While there is a relatively large local mini grid industry given the more than 190 mini grids currently installed, we are not aware of any significant partnerships between local and international firms. | In addition to the existing $51 million investment from the WB, alongside FCDO, the WB is also preparing a significant investment in mini grids in the five G5 Sahel countries (final amount TBD), though it is not yet clear how much of the total project amount will be committed to Mali. To date we are not aware of any significant private sector investor interest in Mali’s mini grids market. | The government of Mali has provided some training programs for mini grid operators and engineers, according to a 2017 capacity needs assessment by Kang’ethe et al. | Mali has a relatively strong institutional framework to support mini grids, in particular because the rural electrification agency AMADER has historically been a strong proponent of mini grids, and because the national government has experience supporting mini grid projects through a concession approach. | With a RISE score for mini grids of 75/100, Mali ranks near the top of the list of all countries for which mini grid regulatory framework information is available. Continued support will be needed to ensure that the regulations evolve as the market evolves. | Bureaucratic red tape remains a significant barrier to investment and a major cost to businesses across Mali. With a Doing Business score of 53/100, the country ranks in the middle of African countries in terms of the ease with which companies can start up and operating a business.
Mauritania | A market intelligence report was published in 2019, at: https://greenminigrid.afdb.org |  | FCDO appraising options for support to mini-grid development in G5 Sahel Countries (Burkina Faso, Chad, Mali, Mauritania, and Niger) |  | Of the 70+ mini grids currently installed in Mauritania, at least 20 are solar hybrids, and these were developed within the last few years. This indicates a nascent market for solar hybrid mini grid technologies in Mauritania. | The government of Mauritania recently completed a tender for national electrification planning and this is expected to include geospatial analysis at the national level. It is not known whether local mini grid developers are using geospatial analysis to identify and plan portfolios of mini grids. | To date we are not aware of any large-scale or developer-led initiatives to promote productive uses of electricity on mini grids in Mauritania. | To date we are not aware of any large-scale or developer-driven initiatives to engage with communities served by mini grids in Mauritania. | While there appears to be a nascent local industry behind the 70+ currently installed mini grids, it is not clear whether or how much the local developers are partnering with international firms. More work needs to be done to support both the local industry and foster linkages with international firms. | Alongside FCDO, the WB is preparing a significant investment in mini grids in the five G5 Sahel countries (final amount TBD). It is not yet clear how much of the total project amount will be committed to Mauritania. To date we are not aware of any significant private sector investor interest in Mauritania’s mini grids market. | We are not aware of any large-scale training programs for mini grid operators, engineers, or maintenance workers, though the national utility SOMELEC presumably has formal or informal training programs for its technicians and work crews. | While the main elements of an institutional framework for mini grids exist – there’s a ministry in charge of electricity, an electricity regulator, and two rural development agencies (one for electricity, one for access to services in general), it is not clear how effective these institutions are, or how they fit together to support (or not) the mini grid sector. | With a RISE score for mini grids of 27/100, Mauritania is ranked near the bottom of list of all countries for which mini grid regulatory framework information is available. In parallel with efforts to strengthen the institutional framework, significant work will also be needed to develop a coherent, workable approach to mini grid regulations. | Bureaucratic red tape remains a significant barrier to investment and a major cost to businesses across Mauritania. With a Doing Business score of 51/100, the country ranks in the lower-middle of African countries in terms of the ease with which companies can start up and operating a business.
Mozambique | A package of TA involved developing a mini-grid policy framework, including guidelines for (i) Grid Connection of small renewable energy plants and (ii) GMG guidelines and ESIA Standards. This was supported by FCDO under the legacy GMG programme that closed in December 2019. Standard Power Purchase Agreements and the trainings of officials have occurred in November; the project is now closed. A market intelligence report was published in 2017, at: https://greenminigrid.afdb.org | $10 million for mini grids under the Energy for All (ProEnergia) approved in 2019. Site profiling work for all 151 sites have been completed and bidding document is at final stage of preparation. | BRILHO programme up and running with Mini-Grid component, SNV managing. Tender conducted for GMGs support.
Namibia
Niger | A package of TA includes putting a GMG policy and regulatory framework in place with technical norms, quality control, and institutional arrangements, and providing targeted enterprise development support to GMG developers. A market intelligence report will be published in 2020. https://greenminigrid.afdb.org | $34 million for mini grids under the Solar Electricity Access Project approved in 2017. Under Component 2 -- Rural Electrification through Service-based Solar Hybrid Mini-grids: Contract awards are expected soon for mini-grid operators. Under Component 3 -- Solar PV Hybridization of Isolated Thermal Mini-grids and Expansion of Access: Contract awards for hybridization of existing diesel powered min-grids is expected soon. "Niger Accelerating Electricity Access Project" currently under preparation. | FCDO appraising options for support to mini-grid development in G5 Sahel Countries (Burkina Faso, Chad, Mali, Mauritania, and Niger) |  | Like Mali, Niger is a regional leader in solar hybrid mini grid technologies, with significant investment over the past decade in hybridizing diesel-only mini grids and building new solar hybrid systems. Only 2 companies responded to the AMDA inventory survey, though, with a combined ability to deploy around 80 50kW systems in 3 months. | The government of Niger with support from Power Africa has conducted extensive geospatial analysis for 70 high-potential mini grid sites. These are now uploaded to Odyssey. In parallel, the government of Niger has also conducted a GIS least cost national electrification plan, though the cost assumptions appear to be unrealistically high for mini grids. | To date we are not aware of any large-scale or developer-led initiatives to promote productive uses of electricity on mini grids in Niger. | To date we are not aware of any large-scale or developer-driven initiatives to engage with communities served by mini grids in Niger. | There is an emergent local industry behind the 115+ currently installed mini grids, but it is not clear whether or how much the local developers are partnering with international firms. More work needs to be done to support both the local industry and foster linkages with international firms. | Alongside FCDO, the WB is preparing a significant investment in mini grids in the five G5 Sahel countries (final amount TBD) on top of the $34 million already committed. It is not yet clear how much of the total project amount will be committed to Mauritania. The government is actively looking for investors for the 70 sites for which they have conducted extensive studies. | We are not aware of any large-scale training programs for mini grid operators, engineers, or maintenance workers, though local developers presumably have informal training programs for their technicians and work crews. | The institutional framework for mini grids in Niger is relatively strong. The rural electrification agency ANPER is a strong champion for mini grids, and the government has experience with private sector-led mini grid development through a concession framework. More work is needed to strengthen the institutions, though, to enable the scale-up of mini grids in Niger. | With a RISE score for mini grids of 57/100, Niger is ranked in the middle of all countries for which mini grid regulatory framework information is available. More work will be needed to strengthen the mini grid regulations currently embedded in the concession agreements. | Bureaucratic red tape remains a barrier to investment and a cost to businesses across Niger. With a Doing Business score of 57/100, the country ranks in the middle of African countries in terms of the ease with which companies can start up and operating a business.
Nigeria | USD 200 million AfDB Nigeria National Electrification Project (NEP) was Board-approved in December 2018. Component 1: Mini-grid minimum subsidy tender and RBF (USD 70m); Component 2: RBF for productive appliances (USD 20m); Component 3: EPC and O&M to electrify universities. A portion of the funding is under discussion for reallocation to COVID response efforts. Nigeria Energy Access Fund (NEAF): NEAF will be a climate impact fund that will undertake equity/quasi-equity investments in small- to medium-scale sustainable energy projects that have measurable climate positive and energy access impact. In particular, NEAF will invest in companies developing off-grid solar (OGS), green mini-grid, and small renewable IPP solutions. SEFA has provided a grant to support the structuring of the fund. A market intelligence report as published in 2018, at: https://greenminigrid.afdb.org | $150 million for mini grids under the Nigeria Electrification Project approved in 2018. Progress includes qualification of 15 mini grid companies with 71 mini grids (including 3 that have already been commissioned) that will collectively serve 42,611 connections, or 221,577 people, with 5.8 MW of solar PV capacity. The first mini grid was commissioned just 60 days after grant agreement signing, with the State Minister for Power, World Bank Country Director and other dignitaries attending the ceremony. | FCDO Solar Nigeria coming to an end but still supporting clinic/school electrifications, wider Nigeria Infrastructure Advisory Facility phase 2 could support on policy side |  | A global survey by AMDA revealed that more than 140 companies currently operating in Nigeria could have more than 4,000 50kW solar hybrid systems available in 3 months. This is much larger than any other African country in the survey and reveals that the market for solar hybrid technologies is already mature in Nigeria. | With support from the World Bank the REA used geospatial analysis to identify hundreds of high potential mini grid sites across Nigeria. Most of the top-tier developers use geospatial analysis software to plan their portfolios as part of the Nigeria Electrification Project. | The Nigeria Electrification Project includes support for productive uses of electricity, and there are a small number of unrelated pilot studies underway (e.g., one by Crossboundary Innovation Lab). However, more work is needed to establish viable supply chains that connect end users with income-generating appliance suppliers and with microfinance institutions. | While most of the leading mini grid developers in Nigeria have in-house strategies and programs to engage with their communities, so far there is limited activity market-wide to engage with mini grid communities and promote mini grid services. More work is needed to develop innovative market-wide community engagement efforts, particularly linked to productive uses of electricity. | There is a strong cohort of local or regional mini grid developers, and larger international companies have already shown interest in the mini grid market in Nigeria. A few local-international partnerships have sprung up, but more work is needed to foster such local-international collaborations. The Odyssey platform is in a good position to facilitate these partnerships. | The WB and the AfDB have collectively committed more than $200 million in grant support to mini grid developers. “Road shows” of the NEP have sparked interest from investors and individual developers have had some success securing debt and equity finance, but to date no “stapled financing” has been secured for the NEP. | A GIZ-USAID-Winrock initiative helped the Nigerian government develop certification courses for solar and hydro mini grid technicians, supervisors, and engineers, including training manuals for trainers. It also facilitated the training of trainers in 12 technical institutions. More work is needed to significantly scale up such programs. | The REA has established an exceptional team to lead the national mini grids program, achieving impressive results already. There is broad support from senior government officials for mini grids. In general the institutional setup for mini grids is coherent and conducive to the NEP’s private-sector led approach | With a RISE score for mini grids of 70/100, Nigeria has one of the most conducive mini grid regulatory frameworks in Africa. These regulations address all the key regulatory issues and have received generally positive feedback from developers and investors alike. Continued support to NERC will be needed to ensure that the regulations evolve as the market evolves. | With a “Doing Business” score of 57/100, Nigeria is in the middle of the pack for countries in Africa in terms of the ease with which companies can start up and operate a business. Some streamlining has reduced red tape for developers already (e.g., environmental approvals), but more work is needed to reduce the time and investment required to navigate bureaucratic processes.
Rwanda | A package of TA support includes mini-grid feasibility studies for up to 20 selected sites and the development of a corresponding roll-out plan. This was supported by FCDO under the legacy GMG programme that closed in Dec 2019. The project has been extended with new consultants engaged in 2020. | $5 million for mini grids under the Renewable Energy Fund approved in 2017. | EnDev Results-Based Financing for GMGs in the country, close to completion
Senegal | A market intelligence report was published in 2019, available at: https://greenminigrid.afdb.org
Sierra Leone | A market intelligence report was published in 2019, available at: https://greenminigrid.afdb.org | $1 million for mini grids under the Energy Sector Utility Reform Project Additional Financing approved in 2013. Pipeline project under preparation: Sierra Leone Electrification Project. | Rural Electrifiation Sierra Leone (RESL) programme live, 54 Community Health Centres electrified, 50 GMGs built and connections being added now, 94 GMGs planned (360k people). In addition, FCDO supporting pilot of Universal Energy Facility led by SEforALL alongside Rockefeller, USAID, and Shell Foundation. Madagascar and Sierra Leone pilot countries.
Somalia |  | $1 million for mini grids under the Somali Electricity Access Project approved in 2018 "Somali Electricity Sector Recovery Project" currently under preparation.
Somaliland |  |  | ESRES programme - 6 hybrid GMGs - 1.9MW solar, 10k customers, 43% tariff reduction achieved in Phase 1. Programme in its second phase but closing in March 2021.
Tanzania |  | $32 million for mini grids under the Rural Electrification Expansion Project approved in 2016. There has been delays in the offgrid electrification programs due to the challenging sector and policy context, which has affected the SPP and REC credit line that are yet to disburse. | GMGs Tanzania no longer making contributions, but programme continuing in spite of policy headwinds with REA and Sida leadership.
Togo
Uganda | A market intelligence report was published in 2018, available at: https://greenminigrid.afdb.org | $1 million for mini grids under the Energy for Rural Transformation III project approved in 2015.
Zambia | A market intelligence report was published in 2018, available at: https://greenminigrid.afdb.org | $6 million for mini grids under the Electricity Services Access Project approved in 2017. | Cities and Infrastructure for Growth Power Performance Improvement programme scoping activities now, mainly grid utility but also wider sector including mini-grids
Zimbabwe | A market intelligence report was published in 2018, available at: https://greenminigrid.afdb.org
Multi-country | Green Mini-Grids Market Development Programme (GMG MDP). AfDB's key set of TA activities to the broader GMG community. Currently in Phase 2 through the end of 2020. The Africa Mini-Grid Market Acceleration Programme, which is the successor to the GMG MDP, received board approval in December 2020 and will be launched in Q1 2021. FEI and FEI OGEF: Debt facilities for off-grid businesses (FEI OGEF), as well as IPPs, C&I, and GMG businesses (FEI). | Mini Grids for Half a Billion People handbook under preparation; Covid-19 energy access response; support to preparation of the G5 Sahel countries project (with FCDO). | TEA (State of the Market Report, SEforALL Mini-Grids Partnership, Mini-Grid Funders Group, Cross Boundary Innovation Lab, Shell Foundation TIME portfolio (inc AMDA, Odyssey, Spark Meter, Nayo, Equatorial Power) - Steven Hunt overall contact Low Energy Inclusive Appliance (LEIA) - able to support on mini-grid productive use appliances (Jenny Corry at CLASP main contact). More info at this blog: https://minigrids.org/5-years-on-from-the-launch-of-green-mini-grids-africa-whats-been-achieved-and-what-have-we-learned/ | Wide range of support, co-ordinated via Mini-Grids Funders Group